## Slide 1: Canadian Council on Geomatics (CCOG) Work plan 2025-2026
DRAFT December, 2024

## Slide 2: Working Groups

## Slide 3: Canadian Geodetic Reference System Committee (CGRSC)
Purpose: To plan and coordinate inter-agency maintenance and improvement of the Geodetic Reference System in Canada and to promote and facilitate the use of the System as the basis for surveys, mapping, and management of spatially referenced information and related activity.
Activities:
  Facilitate adoption of North American Terrestrial Reference Frame of 2022 (NATRF2022) and update of Canadian Geodetic Vertical Datum of 2013 (CGVD2013) across all jurisdictions in the context of the modernization of the Geodetic Reference System
    Milestone: Aim for a unified adoption of the modernized reference systems (NATRF2022 / CGVD2013) across all jurisdictions by 2030
  Work with provinces (6/10 provinces currently have plans) to develop detailed modernization plans for their respective reference systems

## Slide 4: Cadastral Forum Committee (CF)
Purpose: To facilitate collaboration among provincial, territorial, and federal officials to address and resolve issues in cadastral survey systems, standards, and data integration, while monitoring emerging initiatives and case law to inform policy recommendations and support effective land administration.
Activities:
  Analyze and monitor cadastral survey systems, standards, and legal developments to recommend solutions that improve land administration and align with national and international initiatives.
  Promote ongoing education and collaboration among CCOG CF members on land administration trends, fostering knowledge-sharing beyond formal meetings
  Promote and facilitate the adoption/conversion to North American Terrestrial Reference Frame of 2022 (NATRF2022) in Canada.
  Maintain and replace destroyed monuments for the Centennial Monument Project
  Update the Comparative Analysis of Land Administration Systems in Canada

## Slide 5: GeoBase Steering Committee (GeoBase SC)
Purpose: To provide consistent, up-to-date, national geospatial foundational data to support informed decision-making across various sectors, enabling analysis by geographic location for more effective actions, policies, and outcomes for governments, businesses, and individuals.
Activities:
  Continue to develop GeoBase Data Series Activities: Canadian Hydrospatial Network (CHN) to CCOG vote, Medium-Resolution Digital Elevation Model (MRDEM) candidacy, and resolution of outstanding GeoBase Layer recommendations.
  Renew governance instruments – Collaborate with Governance WG: Update GeoBase SC Terms of Reference/Principles, policies and procedures (PPP) to align with modern geospatial ecosystem, emphasize collaboration, and recommend updates for CCOG approval.

## Slide 6: Governance Working Group
Purpose: To facilitate/lead governance renewal, communications and engagement and work plans
Activities:
  Renew governance: lead renewal of Accord (2025) and support refresh of associated governance instruments as needed (e.g. WG ToR, etc)
    Identify and establish plan to fill any gaps in governance/policy instruments
  Monitor WG and TT activities in support of work plan delivery
  Facilitate CCOG communications and stakeholder/partner engagement

## Slide 7: Task Teams

## Slide 8: Geo.ca
Purpose: To provide foundational, authoritative geospatial data and information in a coordinated, collaborative manner across Canada to serve the needs of Canada’s citizens and contribute to Canada’s social, economic and environmental well-being
Activities:
  Identify and develop new themes for Communities to support P/T needs.
  Develop and curate theme-based content and products to address the needs of communities and support provincial/territorial requirements.

## Slide 9: Risk Reduction, Response and Recovery (R4)
Purpose: To improve national data collections, share best practices, leverage standards and align collaborations, infrastructure and systems to consistently and seamlessly deliver geospatial data and services at the time of need, for disaster risk reduction (DRR) and emergency management (EM)
Activities:
  Define set of actions from Annual General Meeting workshop outcomes
  Complete at least 1 prototyping activity over the upcoming year
  Begin discussions on what desired best practices are
  Fostering collaboration between geomatics and public safety / emergency management communities
  Develop a Geospatial Interoperability Framework for Emergency Management: to provide guidelines that Canada’s emergency professionals can follow to maximize discovery, access, sharing and use of geospatial information for emergency management.

## Slide 10: Standards
Purpose: To advance a framework for national standards coordination, identify priority standards and support their implementation by CCOG members, where needed, to advance data interoperability and integration
Activities:
  Coordinate with TBS to realize modernized Standard on Geospatial
  Identify core standards for inclusion in the modernized instrument
  Conceptualize and develop reference materials to help members implement core standards
  Communicate standards activities and impact

## Slide 11: Technologies
Purpose: To work towards common, integrated solutions for data and technologies, to reduce duplication and realize efficiencies
Activities:
  Select and confirm survey tool (e.g., Qualtrics via Natural Resources Canada) and launch survey to develop a picture of technologies/solutions used by CCOG members and identify needs/gaps that the TT can help address
  Deliver detailed national geomatics technology report to CCOG, potentially annual or online.
  Determine short and long-term data storage solutions and to develop a plan for regular inventory updates (e.g., quarterly by CCOG members).
  Prioritize pain points (e.g., enterprise agreements, SDI platform architecture), execute Proof of Concepts, and continually assess and update priorities.

## Slide 12: Next Generation 9-1-1 (NG-911)
Purpose: To understand and report back to CCOG on the state of readiness of National Datasets which may source back to P/T jurisdictions in the collection and dissemination of datasets required; and to support Location based needs for implementation of Next Generation 9-1-1
Activities:
  To be reestablished in the future